## Sheet1
This template is provided as a free download by Ian Anderson from handycrowd.com. All rights reserved, but feel free to share…
The Plan
Project Title:
Start Date: |  | Expected Finish Date:
Project Brief:
Material and Labour Calculations
Description | Calculations etc for Quantities of Materials | Total number of Units | Unit cost | Material Cost | Days Labour for one man | Any extra Labour Costs | Total of Materials and Labour
Clear the area. Sort out tools and equipment.
Waste container ordered?
Excavate topsoil. Waste container ordered?
Set out the building outline.
Excavate foundations. Book excavator.
Steelwork in foundations
Peg concrete levels.
Concrete founds. Calc. Quant. LxWxD + 10%
Brick/blockwork to ground level.
DPC
Remove dumpling and backfilling
Hardcore subbase and compact.
Sand blinding
Compactor for sand blinding.
DPM
Floor insulation
Slab reinforcement
Cast concrete slab.
Calculate conc. quantity LxWxD plus 10%
Drains and manholes
Excavate soakaways and pipe runs.
Profiles/ tie in brickwork or chop toothings.
Build brickwork up to first floor level.
Blockwork up to first floor level.
Wall ties.
Cavity wall insulation.
Insulate reveals and Vertical DPC.
Door frames.
Window frames.
Lintels.
Install first floor joists.
Install strutting, noggins and brick infills.
Fireplace, chimney and flue.
Staircase and balustrade
First floor straps
Brickwork to wallplate
Blockwork up to wallplate.
Wallplate straps and fixings
Ceiling joists
Rafters
Purlins
Wind bracing
Ridge, hip and valley base
Or prefab. Roofing trusses if using.
Brick/blockwork to gable end
Gable end straps
Valley timbers
Lead to valley
Fascia, barge boards and soffit
Roofing felt
Tile laths
Insulation, fixings if warm roof.
Verge strips
Roof covering, tiles etc.
Leadwork to chimney
Mortar for building work, sand, cement, plasticisers
New openings, lintels etc
Floorboards or chipboard
Timber studwork partitions
Plasterboards for studwork
Internal door frames
Plasterboard ceilings
Loft insulation
Form loft access
Electrical work
Plumbing work inc. SVPs
Plastering sand and cement
Plasterers angle beads, thin/thick
Plasters for finishing works
Screed, sharp sand, mesh and cement
Doors
Door furniture
Glass and putty/strips
Skirtingboards
Architrave’s
Dado or picture rails
Windowsills int.
Kitchen units
Bathroom suite
Nails (whole job)
Screws (whole job)
Mastics, silicones and glues (whole job)
Gutters and downpipe
Floor coverings
Pavings/ landscaping
Paint and decorating works
Misc. skips
Clear away site
Misc. or special order items….
Provisional sums
SubTotals
Summary of costs
| Sub total |  | VAT |  | Total
Materials
Labour.
Provisional sums or costs
% profit and overheads
Total Costs: